## LETTER
OFFICE OF THE PRINCIPAL AND DDPI(DEVELOPMENT), DISTRICT INSTITUTE OF EDUCATION AND TRAINING, CHICKBALLAPUR. / No. Est.1/Pr.pl.app/2010-11 Date: 29-04-2011 / To, / The Member Secretary, / Karnataka Jnana Ayoga, / Bangalore. / Sir, / Sub: Submitting the Project proposal of our DIET with budget. / We have prepared a project on Building Vision about School for Teacher Trainees and Constructivism approach in curriculum transaction. This is being prepared following the suggestions and guidance provided to us during the course of different meetings at DSERT. / The estimated budget for the project is Rs. 5,19,720. We will complete the project by the end of August 2011 as scheduled. We require external support in carrying out this project from KJA and its academic allies. Anticipating your support and guidance, we hope to take up and complete the project in the stipulated time. / With regards, / (B.P. Venkatesh) / Principal and DDPI(devpt), / DIET, Chickballapur.

## Activity_Plan
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, CHICKBALLAPUR DISTRICT, CHICKBALLAPUR.
SL NO	ACTIVITY	DESCRIPTION OF ACTIVITY (WHAT)	WHO	BY WHEN	WHERE	REMARKS
1	Preparatory activities for the Teacher Educators.	Workshop – NCFTE/NCF implications, discussions with teacher educators.	Anchor: Principal, DIET.	9Th & 10th May-11	DIET, Cbpur.	Participants 10 DIET faculty, 2 each from 3 colleges
2	Preparing tools to capture the teacher trainees ideas about schools.	Brain storming/Tool preparation.	TK Raghavendra/ P.B. Basavaraju	12th May	DIET	All DIET faculty, 2 teacher educators from 4D.Ed., institutions.
3	Identifying Institutions and participants	Sending letter to institutions and identifying tr trainees.	Venkataramanappa	2nd May	DIET	One active teacher educator from each of the selected D.Ed., college will be identified for this project.
4	Piloting and administering the tools	Administering the tools to the selected trainees.	TK Raghavendra, Nasrin Taj, Lakshmamma	20th May	Concerned institutes	While this is in progress, DIET Senior lecturers will visit the Institutions and provide the necessary guidance wherever required.
5	Monitoring and Evaluation	Project review meeting	Venkatesh B.P. Principal	23rd May	DIET	DIET Principal will review the progress and take feedback about the total process. Everyone in the project will attend.
6	Data capturing using the tools	Administering the tools in the selected colleges/FGD	Venkataramanappa, Haseena Begum, Sumitrabai	30th May	Concerned institutes	DIET Senior lecturers will visit the Institutions to monitor the process.
7	Specific inputs based on NCF-2005	3 Workshop and 1-field visits to schools	TK Raghavendra/ P.B. Basavaraju	10th July	DIET & colleges.	Visit to an alternative school to see how the specific inputs based on NCF are implemented. Information will be collected using some tools. A discussion will be held.
8	Data capturing using the tools	Administering the tools in the selected colleges/Group discussion	TKR/VR/NTH	17th July	Concerned institutes	This is done after the completion of the initiated process in the institutions. This is followed by group discussions.
9	Analysis	Analysis of the results obtained -comparative analysis	TK Raghavendra.	27th July	DIET
10	Report writing.	Self evaluation about the process and report preparation.	Principal, DIET./TKR	14th Aug	DIET
11	Self evaluation
12	Interim report	Sending the interim report to KJA		30th June

	Preparing training modules in Curriculum transaction
1	Identification of topics.	Workshop	TKR & faculty from 4 TTI.	2nd July	DIET/Govt TTI	One subject viz., Principles of Curriculum Transaction is identified for this purpose. The topics for Constructivist approach is identified with all DIET faculty and staff of Ded colleges.
2	Preparation of Modules	Planning individually	Respective Tr. Educators	10th July		This will be done on their own which in turn is reviewed from time to time. Expert support is sought from RVEC and others
3	Linking it to NCFTE	Workshop	DIET faculty & RVEC mentors	15th July	DIET & concerned colleges.	Discussions will be held involving experts in the field of teacher education for this purpose.
4	Implementation in colleges	Using the prepared modules in respective colleges.	Respective Tr. Educators	20th Aug	DIET & concerned colleges.	Implementation will be monitored from the Principal and DIET team.
5	Collecting feedback	preparation and administering the feedback mechanism.	Respective Tr. Educators	25th Aug	DIET
6	Reporting and Evaluation.	Collating feedback and report	TK Raghavendra.	30Aug	DIET
					PRINCIPAL AND DDPI(DEVPT), DIET, CHICKBALLAPUR.

## Budget
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, CHICKBALLAPUR.
BUDGET FOR THE PROPOSED PROJECT ON VISION BUILDING.
Activity No	Activity description	Cost factors	Total = 519720	COST	TA	DA	EXTERNAL RP COST	LOGISTICS (FOOD,BEVERAGES)	HIRING LCD	STATIONERY	PHOTOCOPY	Others
1	Preparatory activities for the Teacher Educators.	Workshop – 25 people – 2 days	27560		4500	10000	8000	2550		1510	1000
2	Preparing tools to capture the teacher trainees ideas about schools.	5days – 20 people	33702		4000	15000	4000	7500		2202	1000
3	Identifying Institutions and participants	Correspondence	1000		400	600
4	Piloting and administering the tools	DTP & photocopies	10400		800	9600
5	Monitoring and Evaluation	2 day workshop, 20 people	14946		4000	6000		3000		1246	700
6	Data capturing using the tools	DTP & photocopies	5400					400	5000
7	Specific inputs based on NCF-2005	Workshop-3, people 20, 6 days	49672		6000	18000	12000	9000		3172	1500
8	Field visit to one alternate school	1day, 30 people, hiring vehicle	14050		5250	4000		3000		800	1000
9	Data capturing using the tools	10 day visits, FGD	12750		3800	3000	4000			950	1000
9	Analysis	External statistician/data entry	5400				5000			400
10	Report writing and evaluation.	Reporting, printing, documentation	21000					1000	20000
11	Administrative support		10000

		Preparing training modules in Curriculum transaction
	Identification of topics.	3day workshop, 40 people	48120		10000	18000	6000	9000		2120	3000
	Preparation of Modules		9720				8000			720	1000
	Linking it to NCFTE	3day workshop, 20 people	27000		4000	11000	8000			2000	2000
	Material procurement for classroom activities.	Relevant materials	96000	96000
	Implementation in colleges		6000				2000				4000
	Collecting feedback	DTP & photocopies	6000				4000				2000
	Reporting and Evaluation.		10000					10000

	Infrastructure 15% of the project cost
	MP-3 recorder		3000	3000
	Camera-digital		10000	10000
	LCD Projector		30000	30000
	Net book (1Nos)		15000	15000
	Data card (2 Nos)		4000	4000
	Pen drives (5 Nos)		2000	2000
	Contingency		47000

		NOTE: For each of the workshops all DIET faculty will be involved. (6 Sr. and 4Jr. Lecturers) with other participants. Since, ours is the DIET established in April 2009, it further needs to be equipped. For this, we propose to purchase some necessary items under non-recurring cost. In the overall budget, 8% is the cost for stationary and 10% for CG. 15% is the Institutional cost.
					PRINCIPAL AND DDPI(DEVPT), DIET, CHICKBALLAPUR.

## Objectives
	DISTRICT INSTITUTE OF EDUCATION AND TRAINING, CHICKBALLAPUR.
	PREAMBLE: The Pre-service Teacher Education wing began in our DIET from Sept-2011. It is our common experience and observation that the teacher educators and teacher trainees practice most of the curriculum aspects with much importance on the exams. We are putting forth our efforts to bridge the gap between the theoretical inputs the trainees receive in the classroom and the actual situation they see when they become teachers. We thought of creating a vision for teacher trainees. In this regard we have started some measures also. We started the D.Ed., course with practical experiences for our trainees in the real school situations. Trainees were deputed to schools for 3 days and they were allowed have their own first hand experiences about the school and its academic process. These experiences are being used by our DIET faculty whenever transacting the contents in the classroom. This experiment prompted us to extend the same for all the teacher trainees across the district. In this regard, we have proposed to proceed further with the support of KJA and its academic allies.

	VISION: To create a Vision of School for the Teacher Trainees before they become teachers in schools and developing a Constructivist approach for content transaction in D.Ed., Institutions.

TITLE / Creating a broader vision of school and primary education for primary teacher trainees.
OBJECTIVES
1	Capturing the Image of Primary School and its Academic Functions among Primary Teacher Trainees.
2	Creating modules for teaching based on NCF-2005 approach for Primary Teacher Trainees.

	SCOPE
	5 students each from 4 D.Ed., institutions including DIET, Govt. TTI and 2 Un-aided. - VISION BUILDING.
	All the I year D.Ed., students in the four selected institutions -CONSTRUCTIVIST CLASSROOM.

Contribution back to DSERT from Samartha
1	Creation of tools and procedure to measure attitudinal changes.
2	Modules for constructivist approaches for teacher educators.

	Principles underlying SAMARTHA
1	As much as possible ALL DIET faculty will be involved in designing, implementing the program
2	However a specific project may focus on a specific wing, activity within the DIET
3	The wings also can be thought of as being less porous – so that learnings can be shared across wings
4	Try and see what principles from NCF, NCF TE can inform your project design
5	DIET can review/re-look at their own activities

	Rationale: T he teacher trainees perception of school and primary education is an important factor in increasing the quality of education. NCFs vision of scho0l and primary education is different from the experiences of teacher trainees. Our common observations have shown a lot of gap in what the trainees receive in the classroom and what they practice after becoming teachers. For this if is felt that a broader vision of primary school and education at the teacher training level be developed.