## Activity_Plan
SL NO | ACTIVITY | DESCRIPTION OF ACTIVITY (WHAT) | WHO | BY WHEN | WHERE
1 | Meeting all collaborators | The collaborators develop a common vision of the project | CRPs, BRPs, ECs, IERTs, BRC, DIET faculty(Nodal officers) and other RPs, APCs from DPO’s offices | End of April | DIET, Mysore
They understand their role in the project
They will learn to make use of their mobile phones for establishing continued communication
They learn the possibilities of using the internet in sending information
2 | Provision of mobile currency for three months and pen drives to all functionaries | Collaborators regularly use their cell phones for all communication with the schools and the higher/lower offices | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | Every month up to the end of the project starting from May 2011 | In Nanjanagud Block including nodal officers
3 | Creation of formats for consolidating the educational statistics from the Taluk other than what is available in DISE and preparation of trg kit/reading material | Creation of computarised Teacher Profiles | CRPs, BRPs, ECs, IERTs, BRC, DIET faculty(Nodal officers) and other RPs, APCs from DPO’s offices | May First Week | DIET, Mysore
Creation of computerised formats for consolidating follow up information which include letter formats, tables, classroom observation lists, feedback formats
4 | Creation of email ID for each functionary | They learn to use the computers, email, create, use and save files in text forms and also in spread sheets. | CRPs, BRPs, ECs, IERTs, BRC, DIET faculty(Nodal officers) and other RPs, APCs from DPO’s offices | May 2nd week | DIET, Mysore
Using word files,
Filling up tables
Using the internet
5 | Practising the use of internet | They practise using the internet for sending info and cosolidating data | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | May 3rd week | Private Agencies
6 | Creation of data base by the collaborators | Each functionary learns to create and maintain a database that is relevant for his/her functions | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | Last week of May | Private Agencies
7 | Try out of the communication system created | When the schools reopen the flow of info begins among all collaborators | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | June and July | In the respective cluster
DIET nodal officers monitor the flow of information and ensure that the prescribed time schedule is kept up to.
Anomalies in the system created are identified and necessary changes are made to make the system more effective
8 | Visits by assessment/monitoring team | Every week members of the team visit the block and monitor progress. They also collect data on how the project is being implemented. | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | Every week through out the project period | In the block
9 | Review meetings | Twice in a month at the block to review progress | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | Twice in a month through out the project | Block HQ
10 | Reflections | Collaborators critically examine the usefulness of the system created | CRPs, BRPs, ECs, IERTs, BRC and DIET faculty(Nodal officers for Nanjanagudu),APCs from DPO’s offices | July | DIET Mysore
The monitoring officials will compare the project information with information from other blocks

## Budget
Activity No | Activity description | No of days | Cost factors/No of Participants | TOTALCOST | Facilities | TA | DA | EXTERNAL RP COST/RPs cost | LOGISTICS (FOOD,BEVERAGES) | HIRING LCD/computer lab | STATIONERY | PHOTOCOPY | Others
Workshops/Training
1 | Preliminary Workshop | 2 | 40 | 44000 | 0 | 12000 | 8000 | 8000 | 6000 | 5000 | 2000 | 1000 | 2000
2 | Creation of formats | 2 | 20 | 30000 | 0 | 6000 | 4000 | 8000 | 3000 | 5000 | 1000 | 1000 | 2000
3 | Training in Using media | 4 | 40 | 85000 | 0 | 24000 | 16000 | 16000 | 12000 | 10000 | 4000 | 1000 | 2000
4 | Creation of database | 2 | 40 | 44000 | 0 | 12000 | 8000 | 8000 | 6000 | 5000 | 2000 | 1000 | 2000
5 | Workshop for Reflections | 2 | 40 | 44000 | 0 | 12000 | 8000 | 8000 | 6000 | 5000 | 2000 | 1000 | 2000
6 | Sharing experience | 6 | 40 | 110000 | 0 | 36000 | 24000 | 24000 | 18000 | 0 | 6000 | 2000 | 2000
7 | Workshop for tools/book kit preparation | 1 | 10 | 11500 | 0 | 1500 | 1000 | 4000 | 750 | 4000 | 250 | 0 | 0
Providing Support Facilities |  |  |  | 0 |  | 0 | 0 |  | 0
6 | Mobile currency | 120 | 40 | 96000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Using browsing Centre Facility @Rs.30 per hour, 2 hours a day | 10 | 40 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Using database and other communication - PC & internet required | 60 | 40 | 144000 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Training kit - booklet Preparation and copies | 0 | 40 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring and evaluation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Monitoring/ assessment team visits | 12 | 4 | 12000 | 0 | 7200 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
11 | Documentation/Analysis/ reporting by assessment team |  |  | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Cost |  |  | 664500 | 282000 | 110700 | 73800 | 76000 | 51750 | 34000 | 17250 | 7000 | 12000
Infrastructure 15% of the project cost
1 | One laptop with bsnl datacard for nodal officer | 0 |  | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | providing pen drives @ Rs.300.00 each | 0 | 40 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Four notebooks | 0 |  | 60000 | 60000
3 | Total infrastructure Cost |  |  | 107000 | 107000
| Total Project Cost |  |  | 771500
| 15% Institutional fee |  |  | 115725
| Grand Total |  |  | 887225

## Objectives
Strengthening the linkages between DIET and the sub district level functionaries
OBJECTIVES
1 | To explore ways of establishing two way communication among all functionaries using mobile phones and the internet
2 | To create a network of educational functionaries wherein information can be transmitted from one point to another in real time.
3 | To train the functionaries in making use of technology for strengthening linkages
4 | To create master formats wherein all data pertaining to all levels of the educational system are readily available for analysis and use for any stakehoder.
SCOPE | All CPRs, BRPs, EC, IERT, BRC, BEO and DIET nodal officers
Contribution back to DSERT from Samartha
1 | Modalities of creating a network of educational fucntionaries for efficient working of the system
2 | Formats that can be commonely used by all functiionaries for collecting and consolidating data to get first hand data
3 | A model for facilitating two way communication among all functionaries in the state
Principles underlying SAMARTHA
1 | Creating a shared vision among all funcitonaries will result in better role perceptions
2 | Creating a forum for sharing of experiences and expectations will create a sense of togetherness among all collaborators
3 | Facilitating free flow of information among all stakeholders will help overcome communication gaps

## Sheet1
Activity No | Activity description | No of days | Cost factors/No of Participants | TOTALCOST | TA | DA | EXTERNAL RP COST | LOGISTICS (FOOD,BEVERAGES) | HIRING LCD | STATIONERY | PHOTOCOPY | Others